## Munka1
Activites in TTT project | desciptrion | sub-activities
A 1 | Activity cluster 1 related to Output 1:
A 1.1 | A1.1: Studies on the ecological and social impact of sustainable procurement of food
| At the early stages of the project, seven studies are carried out. This research provides the whole consortium with additional expertise on sustainable procurement and information on subsequent activities of the project. The studies provide information for dialogues and consultations held with procurers (A1.3) and are the basis for publications (A1.4, A5.2). They are primarily disseminated to TG2 and TG6. CIR carries out a baseline study about the status quo of sustainable food procurement in the EU. The results provide information about the needs and constraints for procurers within the EU and allow for a needs-oriented capacity building approach in workshops and dialogue events. Additionally, CIR (1), Dortmund (2), BRF (1), CS (1) and Cluj (1) carry out 6 studies on national and local research gaps identified before the start of the project, including on the availability of sustainable products, obstacles to SFP, the monetarisation of positive ecological consequences of sustainable food, and healthy community catering as a lever to reach more inclusive societies. A third party CSO from Guatemala conducts studies (3) on effects of global supply chains as well as the potential of agroecology as sustainable alternative. Partners may translate and adapt studies into their own local context. | Baseline study about the status quo of sustainable food procurement in the EU
Studies on national and local research gaps identified before the start of the project, including on the availability of sustainable products, obstacles to SFP, the monetarisation of positive ecological consequences of sustainable food, and healthy community catering as a lever to reach more inclusive societies
Third party CSO from Guatemala: conducts studies on effects of global supply chains as well as the potential of agroecology as sustainable alternative.
A 1.2 | A1.2: Legal opinions on different possibilities of public procurement of sustainable food
| Four legal opinions are commissioned to experts on procurement law. The legal opinions explore new possibilities for the sustainable procurement of food in European as well as national regulations. The findings on the European procurement regulations are provided to the LAs in all five countries. The legal opinions are published as online publications and presented in exchange events and online forums on public procurement to promote new tools for SFP. In total, 1,000 decision makers and public employees of TG 2 are reached with the findings. The legal opinions are commissioned and published by CIR, BRF, Zugló, CS and Cluj | Commission and publish legal opinions (topics not defined yet)
Commission and publish legal opinion and analyses of Polish regulations on procurement with an aim of providing concrete solutions to the procurers
Commission and publish legal opinion augmenting existing tender documentation to include new green jobs/services
Commission and publish legal opinion reviewing and improving urban gardening HCL
A 1.3 | A1.3: Workshops for decision makers and public administrators in local authorities on sustainable procurement of food
| The workshops aim to impart general knowledge and increase the acceptance of SFP for decision makers and public procurers in LAs. Positive environmental and social impacts of SFP and concrete measures for procurement processes are addressed. The WS especially addresses young employees and trainees as they are the ones to bring the cultural change for sustainable procurement into the administrations. 18 workshops are carried out in all countries (DE, PL, RO, HU, IT); 350 participants of TG 2 develop profound knowledge on the positive impact of SFP. To increase the impact, LA partners invite other local authorities. BMA (2), Zugló together with TVE (3), Bergamo (2), Dortmund (3), CIR (2), CS (4), Cluj (2) organise workshops. | Organise workshops (LAs: provide knowledge on public procurement, CSOs: focus on sustainability issues)
Carry out Sustainable Procurement Days in 2024, 2025 and 2026 for municipal and non-municipal procurers
Give workshops for 20 additional Local Authorities in Germany and inform them about good practice examples regarding the procurement of fair food.
A 1.4 | A1.4: Information material for decision makers and administrators in local authorities and private institutions on measures for a sustainable food system
| Information materials like leaflets, brochures and booklets support the workshops (A1.3) and give decision makers and employees practical advise on how they can carry out concrete projects in the three categories of projects for sustainable food systems (see A2.4). 500 people of TG 2 are reached through the information materials. CS, CIR and Dortmund publish three information materials in the second project year | Elaboration of information materials like leaflets, brochures and booklets
A2 | Activity Cluster 2 reakted to Output 2:
A 2.1 | A2.1: Resolutions on sustainable food
| All LAs contribute to new or improved resolutions on sustainable food. Resolutions on municipal level are an important tool to increase commitment by local administrators. Resolutions might entail that certain food products for local institutions have to be procured fairly or of organic quality. Resolutions build on the research results obtained with studies (A1.1) and legal opinions (A1.2). By setting the framework for local decisions, municipal resolutions have the potential to improve sustainable food systems and make peoples’ access to healthy food in public institutions mandatory. Where possible, the youth is consulted in the process of passing new resolutions to ensure that the demands of young people are included in political frameworks. All LAs initiate processes on municipal resolutions. CSOs contribute with their expertise on human rights and environmental consequences of unsustainable food as well as advocacy work. | Initiate processes on municipal resolutions.
Contribute with expertise and avocacy
A 2.2 | A2.2: Trainings on sustainable public procurement of food, food waste reduction and self-supply of food for key stakeholders to develop concrete projects
| Decision makers of the LAs, public procurers, employees of institutions, kitchen staff and consumer representatives participate in trainings to develop concrete local projects on sustainable food systems in three categories: 1) sustainable food procurement (SFP), food waste reduction and food self-supply. In these trainings they develop the local projects (A2.4) and concrete measures for their implementation and monitoring. Young stakeholders bring in their perspectives and ideas. Young representatives may be trainees of the LAs, young activists and representatives of universities, schools, and sports groups. Trainings are coordinated between LAs and CSOs in every country. BMA, Zugló, Dortmund, Cluj, Bergamo, BRF, and CS carry out co-creation workshops in DE, PL, HU, IT, RO with kindergartens, schools, universities and other education institutions, youth centres, hospitals, and other institutions with collective catering | carry out co-creation workshops in DE, PL, HU, IT, RO with kindergartens, schools, universities and other education institutions, youth centres, hospitals, and other institutions with collective catering.
carry out workshops for food procurers of kindergartens and other education institutions
give workshops to review the current public catering procurement practice for the procurement office and other municipality staff.
conduct workshops with representatives of universities and catering services supplying schools, kindergartens and hospitals.
give workshops for schools and other education institutions
A 2.3 | A2.3: Dialogue events between public institutions, local farmers, suppliers of fair and organic food, bundlers, and logisticians to identify measures for sustainable food services
| LAs and CSOs carry out dialogue events with catering companies, suppliers like fair trade companies, and organic farmers to discuss the concrete local food projects, especially those on public procurement and food waste reduction. For example, they present concrete tender documents and answer the questions of farmers and companies. Other dialogues aim to address the current challenges faced by local farmers and suppliers of fair food to enter public procurement markets. 100 companies and farmers (TG 4) are reached with dialogues and consequently have more clarity about the requirements of the tender documents. BRF (2), BMA (3), Dortmund (3), TVE (2), CS (10) and Cluj (3) carry out dialogue events. | carry out dialogue events with catering companies, suppliers like fair trade companies, and organic farmers
A 2.4 | A2.4: Fifty local projects on sustainable food systems that contribute to sustainability, a more inclusive society, and AR of the interdependent world
A strong alliance between CSOs and the LAs develops and implements 50 local projects on sustainable food systems in three categories: sustainable procurement of food, reduction of food waste and self-supply of sustainable food. 50 projects will provide 200,000 recipients in public canteens with healthy and sustainable food, e.g., in schools, universities, youth centres, kindergartens, hospitals, and other public institutions.
| A2.4.1 Twenty local projects on sustainable procurement of food and catering services LAs and CSOs support (public) procurers and canteen staff to develop tenders for products produced under high human rights and ecological standards, like fair trade products (for example coffee, cacao, tea, sugar, rice and banana), and organic and regional food (vegetables, fruit, cereals, milk products). Young trainees who are involved with procurement are included in the projects as well as recipients of the food and CSOs. BRF, BMA, Zugló, Bergamo, CS, Cluj, and Dortmund carry out or initiate local projects on SFP such as introducing more plant-based meals, establishing a sustainable food label for Horeca (hotels, restaurants, cafes) and setting up new and improved digital structure to procure sustainable food preferentially in DE, IT, PL, HU, RO. | Local projects on SFP
Implement local projects on SFP involving kindergartens and education institutions in pilot projects on public procuring of fair and sustainable food.
Implement local projects on SFP involving nurseries and people’s kitchens in procurement processes.
Implement local projects on SFP involving restaurants, school canteens and bars in the “Menù Green” offering vegan tables with a lower ecological footprint to the guests, especially young people.
carry out a pilot project introducing fair trade products in the administrations of the cities and two kindergartens
carry out procedures for sustainable procurement in every project year, digitise the ordering process so that sustainable food can be procured preferentially and take measures to centralize food procurement.
Develop pilot projects implementing fair and sustainable food procurement
| A2.4.2 Fifteen local projects for the reduction of food waste The applicants carry out 15 innovative and creative projects to reduce food waste in public institutions and restaurants. The organisation Feedback EU recently showed in a study that more food is thrown away in the EU than the EU imports, producing 6% of the EU’s greenhouse gases. As food waste reduction allows institutions to save money, it also enables them to choose more sustainable products, thereby providing more consumers (TG 1) with sustainable food in the sense that less food waste causes less ecological and social impact. Every LA carries out projects on food waste reduction, supported by the CSO partners. Youth participation is of particular importance, youths’ ideas for innovative projects are included in the project design as some partners open contests for innovative ideas that will be put into practice. The youth are expected to participate as food waste is an emotional issue which they want to mitigate, as initiatives like foodsharing and TooGoodToGo clearly demonstrate. BRF, BMA, Dortmund, Zugló, Cluj, Bergamo, CS, and Mani Tese carry out or initiate projects in DE, HU, IT, PL, RO; addressing menu engineering and leftover policies of public institutions, restaurants, festivals, and markets; supporting local food sharing initiatives; and organising leftover cooking events. | Projects on the reduction of food waste
Carry out an innovative project with public institutions in Warsaw, setting up and promoting fridges in public spaces where everybody can put food in order to share food and avoid food waste
conduct a project on food waste with the local association of restaurants
support the existing network “Food Waste Saving” and carry out public left-over cooking event in cooperation with the adult education centre.
cooperate with festivals to develop food waste policies
carry out two workshops to reduce food waste and establish public food sharing spots
Carry out a call for proposals for youth (during the worksho A2.0) to propose local projects on food waste reduction, implementing the most convincing ideas
carry out a review of the procedure of waste reduction in two schools, create campaign content for schools and public administration on food waste and connect local administration with local food banks
operate in two different districts of the city of Milan to reduce food waste in open-air market, recovering unsold food, select it and share it with all the people who participate in the activity
| A 2.4.3 Fifteen local projects on self-supply of sustainable food Local projects on self-supply especially involve young people and people less involved with global challenges in a participatory, creative, and motivating way. The projects implement the ecological and social principles of agroecology. The own cultivation of food improves the appreciation of food, demonstrating the time, effort, and resources that go into growing food. This in turn also motivates participants to reduce their own food waste at home. On the other hand, the project supplies institutional kitchens with fresh, healthy, and sustainable food. Every LA carries out projects on food self-supply supported by the CSO partners. BRF, BMA, Zugló, Dortmund, Cluj, Bergamo, CS, and Mani Tese carry out or initiate projects in DE, HU, PL, IT, RO, including gardens and wicking beds in schools and public institutions, community gardens, green houses that are built together with youths, courses on organic horticulture, as well as one “world field” (DE) together with the Open-Source-Seed Community where the production of local produce in the city is accompanied by educational programs | Projects on food self-supply
establish gardens and wicking beds offered to schools and public institutions for gardening of vegetables and herbs to be used for the canteens.
establish green houses for local schools
involve kindergartens in the “grow your own” campaign
promote two local food markets and two community gardens through awareness raising activities.
carry out a diversity of projects building a community of local producers; for example allotment garden associations and the Open-Source-Seed-Community; establishing eco-farms in the city
connect a local school with the Botanical Garden
offer courses in organic horticulture
carry out self-supply projects with the University of Agriculture, 3 kindergartens and schools (e. g. on niche production in buildings) and public canteens (on locally produced herbs and spices)
A 2.5 | A2.5: Recipe development (with chefs and a nutritionist) for healthy and sustainable food to be offered in institutions with collective catering offers
| Nutritionists and ecotrophologists are commissioned to develop recipes for sustainable dishes that are ideal for public canteens (i.e., healthy, sustainable, affordable). The recipes are shared with the whole consortium and with public institutions and used in AR materials (A.5). CIR, Dortmund, BRF, CS, BMA, and Cluj participate in recipe development for canteens. | Recipe development for canteens
Develop a cookbook with recipes possible for easy adaptation in collective food institutions
A 2.6 | A2.6: Training on sustainable food for staff in kitchens
| Trainings for kitchen staff ensure that they procure sustainable products and implement the recipes developed in the framework of the project. The trainings are offered to kitchen staff of a variety of public (and private) institutions like kindergartens, schools, universities, hospitals, elderly centres and other institutions. The trainings are also used to familiarise the kitchen staff with the local projects on SFP, food waste and self-supply. In these workshops, young kitchen employees are also shown how they can engage as multipliers and project ambassadors (A.6). In total, 500 kitchen staff (TG 3) are trained on sustainable procurement and healthy and sustainable recipes. Training concepts are developed and implemented by CIR, Dortmund, Zugló, Cluj and CS. | Development and implementation of training concepts
A 2.7 | A2.7: Global Citizenship Education (GCE) events and self-learning
| Public contests for sustainable recipes are an innovative measure to make TG 1 aware of the local projects on sustainable food systems. Next to kitchen staff, nutritionists, students, employees of public institutions, consumers, and farmers from Global South are invited to suggest recipes as a means of sparking their interest in the origin and quality of their food and of generating ownership in and responsibility for sustainable food. Winners of the contest are selected via social media (TG1). The winning recipes are permanently included in the menu of canteens and spread within food blogger networks and food magazines. 10,000 recipients of public food are made aware of sustainable menus in public and institutional canteens through the contest. The contests are carried out by BRF, BMA, Dortmund, CS and Cluj. | Public contests for sustainable recipes
A3 | Activity cluster 3 related to Output 3
A 3.1 | A3.1: Eighteen exchange events between public institutions, local farmers, consumer representatives and suppliers of sustainable food to identify measures for sustainable food services
A3.1 | Exchange events are carried out to identify trend-setting ways for local SFS and services. Common visions for a solidarity network between the stakeholders and joint actions for the future are identified. The events also identify current and future challenges for local projects on sustainable food systems, contributing to the sustainability of the local projects (A2.4) and a long-term cooperation between stakeholders. The focus is on the involvement of young stakeholders. The exchange events are carried out in the framework of big festivals and conferences, thereby reaching a variety of actors and stakeholders, in particular TG 1, TG 2, TG 3, and TG 4. The exchange events are carried out by TVE (2), Dortmund (3), Zugló (2), CS (8), Mani Tese (1) and Cluj (2). | Carry out exchange events
A 3.2 | A3.2: Dialogues between local authorities and political decision makers on the regional, national and EU level on sustainable public procurement of food
| Representatives of LAs and CSOs discuss measures that improve the conditions for SFP with political decision makers, such as improved regulations and regional or national food strategies. A special focus is on the Legislative Framework for Sustainable Food Systems (FSFS) which will be presented by the European Commission in September 2023. Discussions are based on policy papers developed by the consortium. 20 decision makers are informed by local authorities about their need to procure sustainable food and bring this input into their political work. Meetings between these stakeholders contribute to a societal dialogue on sustainable local food systems. Exchanges and policy papers help to harmonise political demands, activities and give orientation for local food procurers. Ten meetings are held by Dortmund, CIR and CS in all three project years | Hold meetings with political decision makers
A 4 | Activity cluster 4 related to Output 4:
A 4.1 | A4.1: Six international conferences to present and discuss best practice examples on sustainable food systems in local authorities
| Six international conferences to present and discuss best practice examples of sustainable food systems are hosted by different LAs. The conferences may be linked to existing bigger conferences such as the “Sustainable Days” in Dortmund, DE, to reach a variety of interested actors and stakeholders. Different LAs within the EU are connected and learn about existing best practices on sustainable food systems, including sustainable procurement of food. Knowledge is thereby be shared beyond the project, allowing other LAs to profit of the project’s expertise. BMA (1), Dortmund (4) and Cluj (1) will host conferences. | Host international conferences
A 4.2 | A4.2: Exchange programme for 30 young trainees between the local authorities
| Each year, each LA partner hosts 2 trainees of a different LA administration while sending 2 of their own trainees to another LA. Through these exchanges, young people training for a position in LA administrations learn firsthand about other approaches on sustainable food systems and sustainable food procurement in EU LAs. As future work generation, trainees are sensitised by innovative approaches and bring back new ideas to their own LA, thereby, best practices are shared within the future generation of public administrators. All 5 LA of the project (Dortmund, BMA, Cluj, Zugló, Bergamo) participate in the exchange programme (DE, RO, HU, IT). Each exchange lasts two weeks. Each LA hosts and sends 2 trainees per year, 6 trainees during the whole project. | Send trainees
Host trainees
A 4.3 | A4.3: Twenty national workshops for the dissemination of best practice examples.
| Best practice examples of SFP, food waste reduction and self-supply with food is shared with all TGs in national workshops to disseminate learnings. Other stakeholders benefit from experiences projects partners made within Turn the Tables. Based on these positive inputs, they are inspired to act and further distribute best practice projects on sustainable food systems. 20 workshops are organised in DE, IT, HU, RO, PL. The workshops mostly take place in the 2nd and 3rd project year, after practical experiences in local projects have been made. | Organise workshops
A 4.4 | A4.4: Publications on best practice examples
| Partners report about their best practice examples in publications to reach an even wider and more heterogenic audience. In addition to print publications, best practice examples are shared via newsletters of the co-applicants and relevant external actors (like city networks), local newspapers, and online features. With this information, other LAs are motivated to implement existing best practice examples in their own cities. CIR compiles a final publication summarising the main successes and best practices achieved within the project in the last project year. All partners report about their local projects in press releases, newsletters, and on their own as well as the international project website. | Report about local projects (in press releases, newsletters, website, etc)
Comply a final publication summarising the main successes and best practices achieved within the project
publish and promote editorial feature contents
A 4.5 | A4.5: Involvement of local authorities and CSOs in Ukraine and in Guatemala in best practice exchanges through financial support to third parties
| The project supports two international third parties: one LA in Ukraine to express solidarity with the country; and one CSO in Guatemala to include a perspective from the Global South. Guatemalan CSO: The main objective of the international third-party support to Guatemala is to include a Global South (GS) perspective. Also, agroecology is practiced much more in Guatemala than in the EU. The CSO contributes knowledge via 3 studies (A1.1) on the detrimental effects of industrial agriculture as well the agroecological countermodel, thereby contributing to SO2. The third party also co-organises speakers’ tours and exposure trips (A5.8, A5.9). CIR publishes the call, evaluates the applications, and selects an appropriate and fitting third party. Ukrainian LA: The objective of the support to a LA in Ukraine is to show solidarity and assist in the reconstruction of the administrative structure, with a focus on sustainable procurement. If Ukraine becomes a full member to the EU, EU public procurement law would apply. Since Ukraine also plays a huge role in the agricultural production of cereal for Europe and the world, the LA shares their experience on the local and global challenges of the current food system and thereby contributing to SO2. The expected result of the support is that a Ukrainian LA develops capacities through best practice exchanges as well as sharing their own expertise with other LAs in the EU (A4.1, A.4.4). If the situation allows for it, women working in Ukrainian agriculture are invited as speakers on the empowerment of women (A5.8). Due to the present situation in Ukraine, some flexibility on the actual involvement is needed. Dortmund publishes the call, evaluates the applications, and selects an appropriate and fitting third party. | Guatemala: publish the call, evaluate the applications and select an appropriate and fitting third party
Ukraine: publish the call, evaluats the applications and selects an appropriate and fitting third party
A 5 | Activity cluster 5 related to Output 5:
A 5.1 | A5.1: Website and information services
| A communication agency sets up a smartphone-friendly international website using the campaign design. The website is the public face of the project, providing condensed information. Online materials, pictures and videos of the local projects as well as calls to action for youth engagement are shared here. Social media channels link to the website and vice versa. All applicants promote the website in addition to also sharing contents of the project via their own national websites, e-mail newsletters, and print magazines. | promote international website
share contents of the project via national websites, e-mail newsletters, and print magazines.
A 5.2 | A5.2: Creative campaigning publications for hospitals, universities, schools, youth centres and public canteens on global challenges of the food system and local/sustainable alternatives (e.g. menus)
| Local projects and best practices are accompanied by print as well as digital campaigning publications. Applicants publish creative publications according to the current communication preferences of the youth target groups, including menu cards, little gift bags for first semester students, consumer guides and travelling exhibitions. To give a face to the often-invisible kitchen staff and procurers and to generate the sentiment of participation and co-responsibility, some publications include their testimonials. In total, 500,000 TG0 are reached on- and offline, made aware of global challenges of the food system and motivated to choose sustainable alternatives. BRF, BMA, Dortmund, Cluj, CIR, and third parties contribute creative publications. LAs implement soft-nudging mechanisms in canteens to inspire consumers to make more sustainable food choices. Creative campaign materials are published in each project year. Some are inserted in relevant print publications as supplements or promoted in external adverts to expand their reach. | Publish creative publications
implement soft-nudging mechanisms in canteens to inspire consumers to make more sustainable food choices
A 5.3 | A5.3: Social media campaign on the global challenges of the food system and local / sustainable alternatives reaching 5 million users
| To reach youth as well as population segments less sensitised to global challenges, the project implements an EU-wide social media campaign, which is co-developed by youth (especially youth studying design or communication), a communication agency and the consortium. To this end the youth is invited to take part in a 3-day-hackathon/design-sprint organised by the lead (Dortmund) at the start of the project (year 1, half-year 1). A common Instagram channel as well as the social media profiles of the consortium reach out to the main TGs. Since algorithms and users favour personal stories and portraits, two to three consortium members are the selected faces of the campaign. In addition, members of the youth task force (A5.10) and youth organisations (third parties) as well as key stakeholders like farmers, cooks, and beneficiaries of the local food projects are invited to appear on the Instagram channel. Successful local projects (A2.4) are promoted via short videos, reels, and other formats according to the media consumption preferences of the TGs. 5,000,000 social media users (TG0) are reached by the Turn the Tables social media campaign. Users are encouraged to ask their local institution on Instagram to cater sustainable food. The content is picked up by young multipliers who share it independently to reach further audiences. A common social media strategy is developed within the first 3 months with the support of a communication agency as well as the youth task force (A5.10). All Applicants and third parties contribute to the strategy by providing and sharing posts. Targeted paid advertising increases the reach of the campaign. | 3 day hackathon / design-sprint
Development of a common social media strategy
A 5.4 | A5.4: Development of a phone app and online map on sustainable food options
| Three partners develop or update existing local digital maps with sustainable food options, including shops, cafés, catering offering sustainable products, food cooperatives, places aimed at food waste reduction, places to share the food, places to get the food for free. 400,000 citizens (TG0) are reached through an information campaign online and via social media. The apps are used by 16,000 TG1, 500 suppliers are included in them (among them producers and farmers – TG4). BRF updates its already existing apps “Where to go?” and “Good shopping”. The latter is a tool for consumers as well as procurers. TVE updates a digital CSA and local solidarity-based food systems map online. Zugló updates their “ökomap” yearly. | Update already existing apps "Where to go?" and "Good shopping"
Update a digital CSA and local solidarity-based food systems map online
Update the "ökomap" yearly
A 5.5 | A5.5: Collaboration with 20 influencers on the global challenges of the food system and local/sustainable alternatives
| In the context of the social media campaign (A5.3), 20 influencers or content creators are involved by project partners to spread the project’s messages to a wider audience on national levels. Influencers also report on the local projects. The selection of the influencers is made carefully to ensure their values align with the values of the project and to minimise the risk of reputation loss. Young people have a lot of trust towards the influencers they follow and are likely to think about a topic proposed by their favourite influencers. This leads to the information of youth on global challenges in the food system and sustainable alternatives. The involvement of influencers contributes to reaching 1,500,000 TG0 of the 5,000,000 A5.3 target and mobilises 100 TG5. Influencers especially contribute to reaching youth and population segments less sensitive to and involved with global challenges. BRF (4), Mani Tese (2), TVE (4), BMA (2), Cluj (1), CS (2), Zugló (3) and CIR (2) involve 20 influencers in total over the course of three project years. | involve influencers in the project
A 5.6 | A5.6: workshops on the global challenges of the food system and local/sustainable alternatives
| Over 200 AR workshops are conducted to inform consumers, especially youth and population segments less sensitised to global challenges, about global challenges in food supply chains and point out sustainable alternatives. The workshops are based on Global Citizenship Education (GCE) as well as “train-the-trainer” approaches. WS are offered in places where the TGs already are, e.g., at festivals, youth centres, in universities and other educational institutions. Students are also invited to field trips to local farmers or producers. Some workshops are offered online. Workshops on food waste are connected to Slow Food’s disco soups as well as foodsharing’s running dinners, where food which would have been wasted by supermarkets is prepared and cooked together. Youth and people less sensitised to global challenges are reached at sports events where AR is added to food offers. Trainings and workshops reach and inform 3000 TG0, 800 TG1, 500 TG2, 50 TG3 and 30 TG5. BRF (2), TVE (4+200 smaller workshops with avg. 5 participants), BMA (3), Bergamo (3), Mani Tese (2), Dortmund (2), Cluj (1), CS (1), CIR (2), Third Parties and trained multipliers (TG5) organise AR workshops during all three project years | AR workshops
smaller workshops (average 5 participants)
A 5.7 | A5.7: Lunch talks on sustainable food procurement in canteens
| LAs organise short lunch talks in their canteens as well as online. Decision makers and employees in LA administrations are informed about global challenges in food supply chains and the need for sustainable alternatives, the important role of women and girls in food supply chains are highlighted. Lunch talks are a fitting format to reach employees in local administrations (TG2) without scheduling extra meetings. They are easy to join during lunch hours (online or in the office) and kept short and concise. TG2 is convinced about the necessity of sustainable food options, as well as measures to reduce food waste. They are inspired to try sustainable dishes and might be motivated to act as stakeholder for more sustainable food systems, e.g., by including sustainable aspects into policies. LAs organise lunch talks, CSOs of the project may be invited as speakers. | organise lunch talks
A 5.8 | A.5.8 Public events on the empowerment of women in agriculture in the EU and the Global South
| CIR and Mani Tese invite female speakers from their partner organisations in Guatemala (CIR) and from different countries in Africa (Mani Tese). Female farmers from the Global South (GS) meet female farmers from IT and DE to exchange views, experiences, and ideas. The focus is on the role of women and persisting gender inequality when it comes to production, access to land etc. TVE organises events with local female farmers, mainly from CSAs and other short/agroecology food supply chains. Female farmers feel empowered and inspired to use new inputs and approaches in their work. The audience at events gets to hear first-hand experiences of global challenges and are sensitised to change their consumption. Mani Tese, CIR and TVE each organise 2 events, distributed over the 3 project years. | Invite female speakers from Guatemala
Invite female speakers from different countries in Africa
Inivte local female farmers
Organize public events
A 5.9 | A.5.9 Three speakers’ tours and one exposure trip from and to the Global South
| CIR and Mani Tese conduct speakers’ tours with speakers from the GS. Experts from the GS participate in the best practices exchanges and knowledge sharing; the tour provides them with a platform in Europe. CIR invites speakers from Guatemala, who also visit CS in Romania. Mani Tese invites speakers from their partner organisations in different countries in Africa. Speakers have a platform to express their demands and report on the effects of the global food system on the GS. The audience at events gets to hear first-hand about global challenges and is sensitised to change their consumption. Young multipliers participate in meetings with speakers for an even deeper exchange. CIR organises an exposure trip with journalists from applicants’ countries to Guatemala. Agroecological projects are visited, as well as locations that demonstrate the destruction done by industrial agriculture. Upon their return, journalists report about the experience. CIR (1) and Mani Tese (2) conduct three speakers’ tours. CIR organises one exposure trip. | Speaker's tour
Exposure trip
A 5.10 | A.5.10 Youth task force participating in and informing the work of the consortium
| In the first project year, a youth task force of 15 TG5 is set up, 3 from each country. The representatives may come from the training programme (A6.2), the university groups (A6.1) or be otherwise selected. The task force is invited to on- and offline co-creation work meetings of the consortium and actively shape the campaign and the common AR activities. The task force acts as “advisory council” to the project which leads to the feeling of ownership of the campaign and its contents for youth. The group dynamic motivates youth to stay active. In addition, incentives such as CV-relevant training is provided. Mani Tese sets up the structure for the youth task force and supervises them during the 3 project years. | Set up the structure for the youth taskl force
supervise the youth task force
A 6 | Activity cluster 6 related to Output 6:
A 6.1 | A6.1: Foundation of Turn the Tables university groups
| Based on the good ties of some co-applicants to university stakeholders, CS sets up two university groups of sustainable food ambassadors in Cluj and Dortmund, together with its student union (which is an associate in this action), sets up a university group in Germany. Highly engaged youth trained as multipliers (TG5) develop and spread the project messages within their universities and related networks. University students are included as stakeholders in AR workshops (A5.6) and in local projects (A2.4). They are also encouraged to join the youth task force (A5.10) to create a link with the youth work within the consortium. 150 TG5 are involved in university groups. The university groups are set up in the second project year by CS, Dortmund and third parties, after the youth task force has been established. | Set up university groups in Cluj
Set up a university group in Germany
A 6.2 | A.6.2 Training programmes for young multipliers
| Based on their experience of the activism schools carried out in the DEAR project “Food Wave”, Mani Tese und BMA develop a training programme with a training cycle for each year of the project on the following 4 topics: (1) agroecology as a new paradigm; (2) economic and political obstacles to the agroecological transition; (3) the strategic leverage of food procurement; (4) community organising and advocacy tools. Other co-applicants can adapt the concept in their own national contexts. 500 youth (TG5) are trained as multipliers for the campaign. While they participate in activities and promote the local projects (A2.4), they also acquire practical skills on campaign and advocacy work and are provided with communication materials to disseminate. Mani Tese sets up a training concept for the training programme. The concept is established in a joint task force of consortium members and tested within the first project year. In the second and third project year, the trainings are conducted by Mani Tese, Dortmund (who cooperate with a new study programme on SFS), BMA, Zugló and Cluj | develop a 4-topic training programme for young multipliers
Set up a training concept for the training programme
Conduct the trainings
A 6.3 | A6.3 Advocacy meetings between young innovators and decision makers on EU and national level
| It is crucial that youth is not only informed and sensitised to global challenges, but they also need a real “seat at the table”. To channel their demands and influence policy on SFS, advocacy meetings between young innovators and political decision makers are organised by CSOs. These innovators are the Turn the Tables food ambassadors: 20 highly engaged youth commit themselves to representing the campaign and also appear on the int. website and social media. They receive certificates which they can use on their CV. CIR and Mani Tese organise two national advocacy meetings. Together, Mani Tese and CIR also organise one advocacy roundtable with MEPs in the European Parliament in Brussels. Synergies with speakers’ tours (A5.9) are used. | organising national advocacy meetings
organising one advocacy round table with MEPs in the European Parlament
A 6.4 | A6.4 Dissemination of and mobilisation for the campaign through providing sub-grants to youth-oriented organisations
| Youth-oriented organisations in all 5 countries of the action join the project in the second year to support the project’s reach to youth and to contribute with their expertise to some activities. | publish a Call for Proposals in the first half of the project year.
be responsible for their national third party and coordinate their work packages in consultation with the Lead Applicant.
A 7 | Activity cluster 7: Overarching activities
A 7.1 | A7.1: kick-of meeting
| The project starts with a 3-day kick-off consortium meeting in Dortmund, DE, in which important decisions regarding working structure, communication work, action plan, and guidelines for monitoring and evaluation lay the ground for the following 3 years. All applicants participate in the kick-off meeting: 2 participants per applicant (=20), as well as third parties and facilitation experts: 3 participants; total: 23 participants | Organization of kick-off meeting
Participants
A 7.2 | A.7.2 Coordination meetings
| In the 2nd and 3rd project year, a 3-day coordination meeting per year takes place in Milan, IT and Cluj, RO. The content and common activities for the next project year (annual action plan) are discussed. The working structure may be revised in parts, to further improve the efficiency. All applicants participate in the coordination meetings: 2 participants per applicant (=20), 1 applicant (10 participants) per third party as well as third parties and facilitation experts: 4 participants; total: 34 participants | Organization of coordination meeting
Participants (per meeting)
A 7.3 | A 7.3 Bi-monthly online conferences
| The consortium holds bi-monthly online conferences (TelCon) via Zoom during the project implementation period. Relevant decisions to which the whole consortium must agree are made. Partners share updates of their implementation. All applicants participate in the TelCons. | Participate in bi-monthly TelCons
A 7.4 | Working Groups and task forces
| At the kick-off meeting, the consortium sets up different working groups and task forces. In these smaller focus groups, partners with special expertise have a monthly online exchange format on topics such as campaigning, joint activities, or local projects. Each working group and task force is led by one partner. These groups/task forces exist for the whole implementation period or are created or finalised when needed. All applicants and contracted third parties participate when appropriate | Set up different working groups and task forces
Participate in working groups and task forces
A 7.5 | A7.5: Networking
| CSOs and LAs integrate the issues and messages of Turn the Tables into their existing coalitions, allowing for a broad dissemination of the messages and encouragement of other actors. Dortmund is member of the working groups on food in both the ICLEI as well as the Euro Cities networks. CIR is member of the network on fair procurement by Engagement Global in Germany. BMA and Bergamo are members of the Milan Urban Food Policy Pact network, Zugló and TVE take part in the public consultation processes initiated by the Budapest mayor local government for the procurement of sustainable food, TVE takes part in the ad hoc working group at the Ministry of Energy responsible for elaborating legal proposals for green procurement. | integrate the issues and messages of Turn the Tables into working groups on food in ICLEI & Euro Cities networks
integrate the issues and messages of Turn the Tables into the network on fair procurement by Engagement Global
integrate the issues and messages of Turn the Tables into Milan Urban Food Policy Pact network
Take part in Budapest public consultation processes for the procurement of sustainable food
integrate the issues and messages of Turn the Tables into working group at the Ministry of Energy responsible for elaborating legal proposals for green procurement.
A 7.6 | A 7.6 Conduct a final external evaluation/MEAL
| A midterm evaluation and a final external evaluation are conducted in the second and third project years, for more detailed information see Implementation Approach. Dortmund oversees the MEAL process. All partners and sub-grantees actively participate. | midterm evaluation
final external evaluation
overview over the MEAL process
actively participate in MEAL
A 7.7 | A7.7: Run three expenditure verifications
| One central expenditure verification is conducted annually to check all partners’ financial reporting. At the start of the project, the lead-applicant, Dortmund assigns an external financial auditor to conduct an annual overall financial audit of the project in line with the EC standard contract. The expenditure verification report is sent to the EC together with each instalment request. Dortmund organises three audits of the financial reporting. All partners and sub-grantees contribute. | assign an external financial auditor to conduct an annual overall financial audit of the project in line with the EC standard contract
Organize audits on the financial reporting
A 7.8 | A7.8: Participation of applicants in the annual EC meetings in Brussels
| Representatives of the project participate in the annual meetings organised by the European Commission/DEAR Support Team for training, exchange of good practice, and networking with other DEAR projects (Exchange Hub, Learning and Development Hub). Representatives of the lead applicant Dortmund and two co-applicants (on a rotating basis) participate. | Always Participate in the annual EC meetings in Brussels
Rotate participation in the annual EC meetings in Brussels